## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Nformi Jinelle |  | j.nformi1@alustudent.com
Emmanuel Dania |  | e.danai@alustudent.com
Onyiwenebi Fiderikumo |  | o.fiderikum1@alustudent.com
Fadlhullah Abdulazeez |  | f.abdulazee@alustudent.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| CNN Policy | Jinelle | 2026-03-17 | Completed | Yes
| MLP Policy | Fadlhullah | 2026-03-17 | Completed | Yes
| Hyperparameter Tuning | Jinelle, Fadlhullah, Emmanuel, Wenebi | 2026-03-21 | Completed | Yes
| Github repository creation | Fadlhullah | 2026-03-19 | Completed | Yes
| README | Jinelle | 2026-03-22 | Completed | Yes
| Demo Video | Fadlhullah | 2026-03-22 | Completed | Yes
| Submission | Jinelle | 2026-03-22 | Completed | Yes
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
2026-03-16 | Discuss assignment, Allocate tasks | Jinelle | Jinelle, Fadlhullah, Emmanuel, Wenebi | Nature of assignments, How to allocate tasks, Timeline for task completion, Submission | Assignment review and submission